# Phase 1 Strategic Plan

Operational Automation

# Executive Summary

We are launching an initiative to automate routine workflows and reduce manual overhead. Three parallel workstreams address distinct bottlenecks:

- Referral Intake: Automate data extraction and missing data collection

- Coach Workflow: Auto-summarize PT notes so coaches focus on coaching

- Clinic Discovery: Understand how to improve scheduling workflows with top 6 partners

ROI: 40-50% productivity gains in intake team + coaches able to handle 20-30% higher caseloads.

# The Problem

## Intake Team

Manually reads referral documents, extracts fields, enters into Salesforce. For fields DocuPipe can't extract, intake staff has no way to collect them efficiently. Result: incomplete cases, delays to patient placement, slower case-to-therapy timeline.

## Coaches

Receive cases going long. Read PT clinical notes manually (10-15 min per note) to understand patient progress. Then decide how to message patient. Time spent reading notes = time not spent coaching. Result: coaches either under-coach or overload with caseload, both harming outcomes.

## Clinic Relationships

Unclear how 6 major clinic partners could improve scheduling workflows. Do they have APIs? Can they reserve slots? Are they open to integrations? Need discovery to understand possibilities.

# Phase 1: Three Parallel Workstreams

## Workstream 1: Referral Intake

Goal:

Reduce manual data entry by 50-70%. Get missing data from patients via Twilio/GoHighLevel instead of manual chasing.

How It Works:

- DocuPipe + built-in LLM extract ~x% of critical fields

- For remaining missing fields, Twilio sends templated text to patient: "We need your employment status. Reply A) Employed B) Self-employed C) Unable to work"

- Patient replies then auto-populates Salesforce

- Intake staff reviews and confirms, case ready for placement

Deliverables:

- Identify 5-10 critical fields DocuPipe struggles with

- Create Twilio message templates for each field

- Integrate Twilio replies with Salesforce

- Pilot with 50 cases, measure accuracy and time savings

Success Metrics:

- Intake time per case: X minutes to Y minutes (target 50-70% reduction)

- Twilio response rate: target 70%+ within 24 hours

## Workstream 2: Coach PT Note Summarization

Goal:

Coaches understand PT note key facts in 2-3 minutes instead of 10-15. Frees up time for actual coaching.

How It Works:

- LLM auto-generates summary: ROM, pain, compliance, functional gains, red flags

- Summary appears in Recovery+ case view with confidence score

- Coach reviews summary (2-3 min) + full note (if needed) then decides messaging

Deliverables:

- Design LLM extraction taxonomy (ROM, pain, compliance, etc.)

- Build summary template

- Pilot with 20 cases, measure coach feedback and time savings

Success Metrics:

- Time per note: 10-15 min → 2-3 min (80%+ reduction)

- Summary accuracy: 90%+ on key facts (coach validation)

- Coach satisfaction: qualitative feedback on utility

## Workstream 3: Clinic Scheduling Discovery

Goal:

Understand how each of 6 major clinic partners could improve scheduling workflows. Map technical and business feasibility.

How It Works:

- Operations/clinic relations team interviews each clinic

- Questions: scheduling system type? APIs available? Can they reserve slots for us? Willingness to integrate?

- Document findings + feasibility assessment for each clinic

Deliverables:

- Interview template (standardized questions)

- Summary document for each clinic: scheduling system, API availability, integration appetite

- Feasibility matrix: which clinics are API-ready? Which need manual workflows? Which are willing to negotiate standing allocation?

Success Metrics:

- All 6 clinics interviewed by Month 3

- Clear Phase 2 roadmap: which clinics to integrate via API, which via standing allocation, which require manual workflow